## Sheet1
|  | June |  |  |  | July |  |  |  |  | August |  |  |  |  | September
Item No | Project Milestone | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18
1 | Research | bar: June Week 1 to June Week 3
2 | Synopsis | bar: June Week 3 to June Week 4
3 | UI Design | bar: June Week 4 to July Week 5
4 | Development Sprints | bar: July Week 5 to August Week 14
5 | Testing | bar: July Week 6 to September Week 15
6 | Demo | bar: September Week 16
7 | Write Up | bar: July Week 5 to September Week 16
8 | Dissertation Proof Read and finalisation | bar: September Week 16 to September Week 18